## Sheet1
COSC1076 ¦ Semester 1 2023
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | Mon-14:30-Vidyut
Group Member: | A | Yiqi Du | Progress Classes: | Ahead
Group Member: | B | Vidyut Venkatesan |  | On-track
Group Member: | C | Benjamin Nippard |  | Behind
Group Member: | D | Andy Than |  | Way Behind
Tutor: | Hongjie Xu
Class: | Mon 2:30pm - 4:30pm
|  | Week 7 | Goals | Tutor Notes | Individual Updates | A | B | C | D
|  |  | Group Formed |  | Weekly Contribution | Join group | Creating group | Join group | Join group
|  |  | MS Team created |  | Issues | Join channel | Creating team channel | Join channel | Join channel
|  |  | Git Repo created |  | Other Notes | Join rep | Join rep | Creating github rep | Join rep
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Individual Updates | A | B | C | D
|  |  | Choice of where to use linked list, vector & array, etc |  | Weekly Contribution | Signal Linked-list for stock list, vector for DTO
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | Create Linked-list and node, implement insert, delete, reset and display methods |  | Added Coin Register object to handle the storing of coins, displaying of coins and resetting of coins
|  |  | Main menu |  | Other Notes | Adding features to main menu options | Created main menu and print all the available options
|  |  | User Prompt (for program), but no/minimal error checking |  |  | stock and load file error checking | Added a user promt and check for EOF value
|  |  | Linked List implementation |  |  | Create Linked-list and node, implement insert, delete, reset and display methods
|  |  | Implementation(s) or suitable ADTs including expected behaviours |  |  |  |  | On-track
|  |  | ADT implementation for storing information |  |  | Implement string compare method when inserting stock |  | On-track
|  |  | Handling coins and stock data files. |  |  | Implement load stock files |  | Implement load coins files
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Individual Updates | A | B | C | D
|  |  | Load/Save to/from data files (doesn't require integration with main menu) |  | Weekly Contribution | Implement save stock files | Created method to save coins into file during exit | Updated Coin Register object to have sorting and printing from least to most
|  |  | Display an item |  | Issues | Implement display items
|  |  | Purchcase an item |  | Other Notes |  | Implemented full purchase method with validation and change return | Added Checks for correct files including wrong number of lines and duplicates
|  |  | Insert and remove an item on the linked list |  |  | Implement delete items | Created add items method to add new items to stock. Purchase subtracts stock by 1 if a valid purchase occurs
|  |  | Write Tests Cases for common uses |  |  |  |  | wrote test cases and expected outputs
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Individual Updates | A | B | C | D
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Compleated all my requirments without errors | Compleated all my requirments without errors | Compleated all my requirments without errors | On-track
|  |  | Full error checking of user prompt |  | Issues | Did full validation of all my requirments | Did full validation of all my requirments | Did full validation of all my requirments | On-track
Other Notes
|  |  | Final Tests |  |  |  |  | Created multiple test cases for program
|  |  | Group Report Written | [5 empty] | write the final report
|  | Progress | On-track
Note on D22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note these are just some random thought on "setting goals". Feel free to set whatever goals your group thinks appropriate here...